# 2nd  progress report meeting

## Thursday, 27th  March 2025

### ONLINE

# List of participants

Prof. dr Ramo Šendelj, University of Donja Gorica, Montenegro

Prof. dr Ivana Ognjanović, University of Donja Gorica, Montenegro

mr Luka Laković, University of Donja Gorica, Montenegro

Prof. dr Jerzy Duda, AGH University od Krakow, Poland

Daniel Schonle, Hochshule Furtwangen University, Germany

Prof. dr Ines Kožuh, University of Maribor, Slovenia

dr Irena Lovrenčić Držančić, University of Maribor, Slovenia

Laura Horvat, University of Maribor, Slovenia

Lidija Milosavljević, University of Montenegro, Montenegro

Jelena Terzić, University of Montenegro, Montenegro

Prof. dr Radislav Jovović, University „Mediterranean“, Montenegro

Prof. dr Marija Janković, University „Mediterranean“, Montenegro

Prof . dr Nataša Gospić, University Adriatik Bar, Montenegro

doc. dr Oliver Popović, University Adriatik Bar, Montenegro

Milena Ljutica, Institute of Modern Technologies of Montenegro

Dunja Bulajić, Agency for Control and Quality Assurance of Higher Education, Montenegro

Total number of participants: 16 from 9 institutions

Meeting was organised through a video conference system ZOOM and it has started at 14h.

Meeting was opened by prof. dr Ivana Ognjanović. She provided with an overall update of the project’s progress and informed participants about administrative challenges resolved within the previous period. Everyone was informed that first payment installations were processed by the officials of coordinating instutition and it should be finalized within the following days.

According to the agenda, representatives from the institutions leading active tasks presented it’s current status, challenges and future plans. Prof. dr Ines Kožuh, from University of Maribor, Slovenia, urged partners to submit technical implementation reports and other required documents for activities that were finalized as it was done for tasks within WP1 and WP10 which they are currently processing.

On behalf of University of Montenegro, leader of T2.2., Jelena Terzic presented current status. She informed everyone that 6 out of 8 national partners reports were collected, with the remaining two expected to be submitted soon. The team agreed to work on a summary document for all 8 institutions. Consortium discussed the challenges faced by the teams in preparing the cyber security reports for each institution. Project coordinator suggested that each institution should have a clear picture of the complexity of the cyber security system. The team requested an additional week for work from the quality control board and a short national meeting next week to provide additional advice on reporting within this task. The meeting was scheduled for next Tuesday (1st April 2025) at 2 PM. Activity leader was instructed to work on the documents relevant for Quality control board, in order for their inspection to be conducted timely.

Prof. dr Jerzy Duda, on behalf of AGH University od Krakow, Poland, informed partners on preparatory activities for the upcoming meeting in Krakow and offered accommodation and transportation advices and help in organization for everyone. AGH will provide with a document containing relevant information about travel and stay at Krakow.

Luka Laković, on behalf of University of Donja Gorica, Montenegro, leader of T10.4. presented activities regarding the project promotion and funcionalities of the website, aswell as the shared platform for dissemination activities progress tracking. He emphasized the importance of correctly categorizing dissemination and communication activities which are to be published on the website. Team also discussed the need to update the dissemination and exploitation plan and the template for tracking dissemination activities, within the T10.1. led by University „Mediterranean“, Montenegro. Prof. dr Radislav Jovović, on their behalf, gave a brief overview of the already conducted activities, ones that were already reported, and urged everyone to timely and properly report according to the dissemination plan. Project coordinator reminded partners about weekly promotions of partner institutions on LinkedIn and outlines the process for future newsletter contributions.

Meeting ended at 16h.

# To-do list:

| Action | Partners | Due Date |
| --- | --- | --- |
| WP1 Fill in sheet Project Boards | Hochschule Furtwangen | 28/02/2025 |
| WP1 Fill in sheet Project Boards | Ministry of Education of Montenegro | 28/02/2025 |
| WP1 - QCM activities for WP2 | University of Maribor | 31/01/2025 |
| WP1 - Planning/Reporting: Inter-Erasmus coaching. | All partners | 27/04/2025 |
| WP2- Submit the first draft of deliverable 2.2 to the quality control board for review | UOM | 04/04/2025 |
| WP2- Organize and attend a short national meeting on Tuesday, 1st April for to provide additional advice on how to finalize report | All partners | 28/03/2025 |
| WP10 - Send the final agenda for the meeting on Monday evening. | AGH | 31/03/2025 |
| WP10 - Review website content | All partners | Online coordination meeting |
| WP10 – Develop methodology for implementation of T10.3 | AUB | Online coordination meeting |
| WP10 – Group all of the contributions for the Newsletter #1 | UDG | Online coordination meeting |
| WP10 - contribute to the Newsletter #1 | AGH, HFU, UBG | 31/03/2025 |
| WP10 – Finalize the design of Newsletter 1 | UNIM | 04/04/2025 |
| WP10 – Send content for partner promotion at project’s Linkedin | HFU | 28/03/2025 |
| WP10 – Report at the shared document: LINK | All partners | Online coordination meeting |
| WP10-Develop rollup and poster for project promotion | UNIM | Online Coordination Meeting |

# Photos: