# Kick-off meeting Minutes – Day I

## Wednesday, 22nd January 2025

### Address: Oktoih 1, Podgorica, Montenegro

### University of Donja Gorica, Montenegro

### Conference room “Vision” 5th Floor

# List of participants

Prof. dr Ramo Šendelj, University of Donja Gorica, Montenegro

Prof. dr Ivana Ognjanović, University of Donja Gorica, Montenegro

Prof. dr Milica Vukotić, University of Donja Gorica, Montenegro

Doc. dr Sandra Tinaj, University of Donja Gorica, Montenegro

mr Luka Laković, University of Donja Gorica, Montenegro

Marija Tomović, University of Donja Gorica, Montenegro

Prof. dr Jerzy Duda, AGH University od Krakow, Poland

Prof. dr Cristoph Reich, Hochshule Furtwangen University, Germany

Prof. dr Ines Kožuh, University of Maribor, Slovenia

dr Irena Lovrenčić Držančić, University of Maribor, Slovenia

Prof. dr Slavko Gajin, University of Belgrade, Serbia

Lidija Milosavljević, University of Montenegro, Montenegro

mr Jusić Lejla, University of Montenegro, Montenegro

Jelena Terzić, University of Montenegro, Montenegro

Prof. dr Marija Janković, University „Mediterranean“, Montenegro

Prof. dr Radislav Jovović, University „Mediterranean“, Montenegro

Prof. dr Srđa Popović, University Adriatik Bar, Montenegro

Doc. dr Oliver Popović, University Adriatik Bar, Montenegro

Aleksandar Šipčić, Ministry of Education, Science and Innovation of Montenegro, Montenegro

Saša Roćen, Ministry of Education, Science and Innovation of Montenegro, Montenegro

Milena Ljutica, Institute of Modern Technologies of Montenegro

Katarina Kovijanić, Institute of Modern Technologies of Montenegro

Tanja Radusinović, Chamber of Economy Montenegro, Montenegro

Nada Rakočević, Chamber of Economy Montenegro, Montenegro

Tatjana Ćalasan, Agency for Control and Quality Assurance of Higher Education, Montenegro

Milica Kavedžić, Agency for Control and Quality Assurance of Higher Education, Montenegro

Dunja Bulajić, Agency for Control and Quality Assurance of Higher Education, Montenegro

Total number of participants: 27 from 12 institutions

Meeting was organised in a Conference Room “Vision” at University of Donja Gorica and started at 9h.

The meeting commenced with an opening address by the project coordinator, Prof. Dr. Ramo Šendelj. Following his welcome to the representatives of the partner institutions, he invited Prof. Dr. Milica Vukotić, Vice rector at University of Donja Gorica and Dean of the Faculty of Information Systems and Technologies, to deliver a welcome message on behalf of the host institution, the University of Donja Gorica.

Prof.dr Ramo Šendelj presented the general information about the project – objectives, work packages and deadlines. After his presentation, all of the partner institutions were presented by their representatives. Partner institution representatives presented general information about the institutions and their role within the project. All presentations will be kept in a shared project folder and could be used for future promotion of CSupMNE institutions.

During the coffee break, the first family photo of the project was created.

The meeting proceeded with the focus on the overall methodology for designing WPs and their relation to defined objectives. Coordinators emphasized the essential importance of understanding existing standards and practices in the field of cyber security, as well as the needs of higher education systems at national and international levels. After the overall presentation of the methodological approach, detailed presentations were divided into two sections: firstly, supporting WPs, WP1-Management and Quality Control and WP10-Dissemination and Community building, and then development WPs, WP2-WP9.

After lunch break, Prof.Šendelj made a comprehensive presentation of the Grant Agreement and drafted the Partnership Agreement. Participants discussed the grant agreement, emphasizing the importance of carefully reading it due to its different rules compared to previous projects. Each partner is responsible for co-financing 10% of their allocated budget, which can include personal costs, subcontracting, or other expenses. The team also noted a new rule where costs can only be covered for each work package after it has been successfully completed. The coordinator's role is to inform the team about these obligations and changes.

The meeting focused on the terms and conditions of a grant agreement, specifically the eligibility criteria, lump sum contributions, and the responsibilities of beneficiaries. There was a discussion about the withholding of payments to beneficiaries if they fail to repay any excessively received grant amounts. The coordinator's role in managing the consortium and ensuring compliance with the agreement was emphasized. The meeting also touched on the obligation of beneficiaries to store information, submit reports, and provide pre-financing guarantees if necessary. The coordinator's responsibilities, including monitoring implementation, acting as an intermediary for communication, and submitting deliverables and reports, were also discussed.

Project coordinator established a coherent work plan for the following period and all of the representatives accepted the work plan in detail.

Meeting ended at 16h.

# To-do list:

| Action | Partners | Due Date |
| --- | --- | --- |
| WP1- Review the Grant agreement, understand the new lump sum financing method and work package-based structure | All partners | 27/01/2025 |
| WP1- Prepare technical requirements for equipment purchases | UDG, UOM, UNIM, AUB | 27/01/2025 |
| WP1- Tax exemption procedure | UDG and inform UOM, UM, AUB | 31/01/2025 |
| WP1- Send email addresses to project coordinator for access to shared Google sheet and Google Drive. | All partners | 27/01/2025 |
| WP1- Inform project partners about key messages received during online CBHE meeting organised by EACEA on 29-30th January 2025 | UDG | Online coordination meeting |
| WP10- Prepare and publish website draft | University of Donja Gorica | 27/01/2025 |

# Photos: