# Kick-off meeting Minutes – Day II

## Thursday, 23rd January 2025

### Address: Oktoih 1, Podgorica, Montenegro

### University of Donja Gorica, Montenegro

### Conference room “Vision” 5th Floor

# List of participants

Prof. dr Ramo Šendelj, University of Donja Gorica, Montenegro

Prof. dr Ivana Ognjanović, University of Donja Gorica, Montenegro

mr Luka Laković, University of Donja Gorica, Montenegro

Marija Tomović, University of Donja Gorica, Montenegro

Prof. dr Jerzy Duda, AGH University od Krakow, Poland

Prof. dr Cristoph Reich, Hochshule Furtwangen University, Germany

Prof. dr Ines Kožuh, University of Maribor, Slovenia

dr Irena Lovrenčić Držančić, University of Maribor, Slovenia

Prof. dr Slavko Gajin, University of Belgrade, Serbia

Lidija Milosavljević, University of Montenegro, Montenegro

Jelena Terzić, University of Montenegro, Montenegro

Prof. dr Marija Janković, University „Mediterranean“, Montenegro

Prof. dr Radislav Jovović, University „Mediterranean“, Montenegro

Prof. dr Srđa Popović, University Adriatik Bar, Montenegro

Doc. dr Oliver Popović, University Adriatik Bar, Montenegro

Aleksandar Šipčić, Ministry of Education, Science and Innovation of Montenegro, Montenegro

Saša Roćen, Ministry of Education, Science and Innovation of Montenegro, Montenegro

Milena Ljutica, Institute of Modern Technologies of Montenegro

Katarina Kovijanić, Institute of Modern Technologies of Montenegro

Tanja Radusinović, Chamber of Economy Montenegro, Montenegro

Nada Rakočević, Chamber of Economy Montenegro, Montenegro

Milica Kavedžić, Agency for Control and Quality Assurance of Higher Education, Montenegro

Dunja Bulajić, Agency for Control and Quality Assurance of Higher Education, Montenegro

Total number of participants: 23 from 12 institutions

Meeting was organised in a Conference Room “Vision” at University of Donja Gorica and started at 9h.

Prof. dr Ivana Ognjanović opened the meeting with remarks on activities concerning WP1.

WP1-Management and Quality Control: The meeting proceeded with the focus on the management and quality control. The project coordinators outlined the structure of the project management and quality control bodies, including the Project Management Board, National Coordination Board, and Quality Control Board. Project coordinators invited everyone to nominate representatives to the board. Prof.dr Ivana Ognjanović emphasized a strict timeline and review process related to the submission of deliverables in order to ensure quality. Dynamic approach to project management was proposed, with regular meetings using video conference systems. Project coordinator will send a Doodle pool in order to establish the day in each month to be scheduled for CSupMNE meetings.

Prof. Ognjanovic explained thoroughly the internal and external monitoring and quality control procedures and presented the methodology which will be used within the process. She presented flowcharts of the work packages which lead to achievement of objectives within the project. Her presentation included straight-forward path to the achievement using this flow chart. All representatives of partner institutions agreed to the proposed flowcharts.

Procedures regarding project management were presented, especially in terms of procedures regarding approach of designing and submitting each deliverable. Activity leaders are expected to finish in accordance to the internal deadline which is due one month before the deadline.  Work package leader’s deadline of controlling and submitting deliverable is ten days after the internal deadline, followed by the deadline for Quality Control Board which is also ten days after WP leader submits the deliverable. At the end, the project coordinator submits the deliverable.

WP2 – Establishment of National Cyber Security framework for MNE HE system: Prof.dr Cristoph Reich from Hochschule Furtwangen University, as a leader of WP2, presented the methodology and expected contributions from partners. He thoroughly presented the approach of design and implementation of activities in the following period.

Following part of the meeting was dedicated to WP3 and WP4 led by the Ministry of Education, Science and Innovation of Montenegro and University of Montenegro, respectively. General ideas behind those WPs were presented as well as expected outputs and results. Participants agreed on more detailed elaborations in next meetings.

WP10-Dissemination and Community building: Meeting focus was then shifted to dissemination and exploitation activities, website development, general dissemination activities, and community building events. The Mediterranean University was identified as responsible for accounts and networks, while UDG will be the coordinator for dissemination activities. The Chamber of Economy is responsible for the design of the newsletter and digital distribution. The team also discussed the organization of nine events at the national level, including networking events, sustainability events, and large project conferences.

In the meeting, project coordinator discussed the importance of aligning the website and newsletters with the project's logo and visibility requirements. They also emphasized the need to comply with Erasmus+ rules about visibility requirements and obligations, whenever and wherever the project is disseminated. The team was reminded to report their activities and involvement in promoting the project. The conversation ended with a discussion on the submission of a dissemination plan and the preparation of the first newsletter.

Participants were informed of strict deadlines of the activities in the following two months and asked to apply the proposed methodology to all deliverables. Discussion on financial reporting methodology followed, in which the project coordinator answered the open questions.

Meeting ended at 16h.

# To-do list:

| Action | Partners | Due Date |
| --- | --- | --- |
| WP1- Nominate representatives for Project Management Board, National Coordination Board, and Quality Control Board | All partners | 27/01/2025 |
| WP1- Reply with preferred choice of dates: SURVEY | All partners | 27/01/2025 |
| WP1- Prepare project handbook draft for partner review. | University of Donja Gorica | 27/01/2025 |
| WP2- Work on analyzing and comparing cybersecurity frameworks for DEV2.1 | All partners (instructions will be sent by Hochschule Furtwangen University) | 27/01/2025 |
| WP2- Organisation and assignment of work | UOM | Next online meeting |
| WP2- Organize online meeting for Work Package 2- DEV2.1 core team | Hochschule Furtwangen University | 31/01/2025 |
| WP10- Dissemination and Exploitation Plan – overall and expected contributions by each partner | UNIM | Next online meeting |
| WP10 – Promotion at institutional websites and social networks | All partners | 31/01/2025 |
| WP10- Organize contributions for newsletter | Chamber of Economy of Montenegro | Next online meeting |

# Photos: