# National Kick-off meeting minutes

## 25th December 2024

### University of Donja Gorica

List of participants

Prof. dr Ramo Šendelj, University of Donja Gorica, Montenegro

Prof. dr Ivana Ognjanović, University of Donja Gorica, Montenegro

mr Luka Laković, University of Donja Gorica, Montenegro

Jelena Terzić, University of Montenegro, Montenegro

Prof. dr Marija Janković, University “Mediterranean”, Montenegro

Prof. dr Radislav Jovović, University “Mediterranean”, Montenegro

Prof. dr Nataša Gospić, University Adriatik Bar, Montenegro (ONLINE)

dr Oliver Popović, University Adriatik Bar, Montenegro (ONLINE)

Marko Vukašinović, Ministry of Education, Science and Innovation of Montenegro, Montenegro

Milena Ljutica, Institute of Modern Technologies of Montenegro, Montenegro

Tanja Radusinović, Chamber of Economy Montenegro, Montenegro

Nada Rakočević, Chamber of Economy Montenegro, Montenegro

Dunja Bulajić, Agency for Control and Quality Assurance of Higher Education, Montenegro

Milica Kavedžić, Agency for Control and Quality Assurance of Higher Education, Montenegro

Total number of participants: 12 on-sight, 2 online, from 8 institutions

Meeting was organised  in a Conference Room “Vision” at University of Donja Gorica and via ZOOM video conference system for the partners who could not attend on-sight, and started at 12h.

The meeting was opened by prof. dr Ramo Šendelj, who welcomed all attendees and expressed enthusiasm for the start of the Erasmus+ project Strengthening the Cybersecurity Posture of the Montenegrin Higher Education System (CSupMNE).

The coordinator highlighted that nationak kick-off is pre-event to the official kick-off meteing which is planned for January 2025. However, the primary goal of this initial meeting is to highlight the importance of cybersecurity in the national education system and the critical need for cooperation and joint measures, especially considering that CSupMNE falls under STRAND 3. Additionally, this meeting is expected to provide a valuable opportunity to share any updates or changes within public authorities that may have occurred since the project's submission in February 2024.

The project coordinator provided an overview of CSupMNE, outlining its objectives, key activities, and expected outcomes. The coordinator also highlighted the project's timeline, emphasizing major milestones and deliverables.

The following sessions were aimed on presenting nevlties in Erasmus+ 2024 projects, compared to previous experience of all project partners. Therefore:

- a comprehensive presentation on the latest Erasmus+ program rules was given by prof. dr Ivana Ognjanović, according to the slight change of rules and regulations. Prof. Ognjanovic presented requirements in terms of project management and reporting, expectations in terms of progress reporting, and responsibilities of the coordinator and partners.

- The project coordinator also presented the CSupMNE budget, detailing allocation of funds across different work packages, and partner institutions share within the costs. Representatives of partner institutions were informed of the proposed funding methodology, and time frame in which transfers of budget will take place.

Participants were given the opportunity to ask questions and discuss any concerns regarding the project implementation, Erasmus+ regulations, and budget distribution. Project coordinator shared best practices for financial reporting and expense justification and proposed time-frame on financial reporting which includes several layers of internal revision.

Special focus was put on presentation of the first draft of the Partnership Agreement and discussion on available options for specific items within it. Partners have agreed to submit their individual comments and suggestions to the project coordinator by January 15th, with the goal of finalizing the Partnership Agreement. The agreement will be discussed during the kick-off meeting and prepared for the signing procedure by the end of January.

The open discussion facilitated a productive exchange of ideas, reinforcing the commitment of all partners to the success of CSupMNE. The project coordinator thanked all attendees for their active participation and reiterated the importance of cooperation and effective communication among partners.

Meeting ended at 14.30h.

To do list by activities:

| Action | Partners | Due Date |
| --- | --- | --- |
| WP1. Internal project coordination at MNE institutions – nomination of contact persons | MNE partner institutions | 10th January 2025 |
| WP1. Kick-off meeting Agenda | UDG | 30th December 2024 |
| WP1. Preparations for Kick-off meeting: understanding assigned tasks, roles and responsibilities | MNE partner institutions | Kick-off meeting |
| WP1. Preparations of Partnership Agreement: comments and suggestions | MNE partner institutions | 15th January 2025 |
| WP1. Preparations of Partnership Agreement: final version prepared for signing | UDG | 31st January 2025 |

# Photos: